## Sheet1
Agile Sprint Planning
Project Name | Ideal Home Locator
Project Manager | Seale Rapolai
Project Deliverable | System that enhances a Real Estate Company’s opparations.
Scope Statement | This system must be able to accurately recommend homes to users using an advanced algorithm as well as assist brokers and managers in their day to day oparations.
Start Date | 2016-08-07
End Date | 2016-10-02
Task Name | Responsible | Start | End | Days | Status
Sprint 1: Problem Statement | Seale Rapolai | 2016-08-07 | 2016-08-14 | 7 | Complete
Feature 1 | Frank C. | 2016-08-07 | 2016-08-14 | 7 | Complete
Feature 2 | Jacob S. | 2016-08-07 | 2016-09-12 | 36 | Complete
Feature 3 | Jacob S. | 2016-08-07 | 2016-08-14 | 7 | Overdue
Sprint 2 | Jacob S. | 2016-09-16 | 2016-09-24 | 8 | In progress
Feature 4 | Alex B. | 2016-09-16 | 2016-09-17 | 1 | In progress
Feature 5 | Frank C. | 2016-09-17 | 2016-09-21 | 4 | Not started
Feature 6 | Shari W. | 2016-09-22 | 2016-09-24 | 2 | Not started
Sprint 3 | Shari W. | 2016-09-25 | 2016-10-05 | 10 | Not started
Feature 7 | Alex B. | 2016-09-25 | 2016-09-29 | 4 | Not started
Feature 8 | Kennedy K. | 2016-09-24 | 2016-10-02 | 8 | Not started
Feature 9 | Jacob S. | 2016-10-02 | 2016-10-05 | 3 | Not started
Create an Agile Project Plan in Smartsheet
Formulas:
Start = [Start, row below]